INGREDIENTIQ

A Practical 16-Week Working Plan

Three-person web-game project | Four-month execution schedule

Project framing. Build a text-first web game in which players guess a food item's NOVA processing level (1-4). The game uses a locally curated food-data snapshot, not machine learning or live API calls during gameplay.

# Team roles

Each person owns a primary area, but all three join the weekly demo, card review, and final testing.

| Person | Primary ownership | Weekly responsibility |
| --- | --- | --- |
| Person A | Frontend and game UX | Game screens, interactions, responsive design, and usability fixes. |
| Person B | Backend, database, deployment | Food/session/response data, game endpoints, exports, and hosting. |
| Person C | Data, research, testing | Card curation, methodology, user testing, pilot coordination, and analysis. |

# Scope rules that keep the project realistic

Use the right term. The available dataset field is nova_group, which represents NOVA processing level. Do not present it as a measured preservative level unless a separate, documented preservative rubric is introduced.

Use only manually approved food cards in the game. Start with 100-150 cards, balanced across Levels 1-4.

Use anonymous session IDs first. Add accounts or login only if the professor specifically requires them.

Do not add machine learning, a live Open Food Facts API dependency, product-image scraping, a leaderboard, or a full admin panel before the MVP works.

If personal information is collected or a formal study is required, confirm consent and ethics requirements with the professor before recruiting participants.

# Four-month overview

| Weeks | Focus | Visible outcome |
| --- | --- | --- |
| 1-4 | Foundation and core game | A real, local 10-question game using approved food data. |
| 5-8 | MVP completion and internal testing | Mobile-ready MVP and a shareable staging link. |
| 9-12 | Pilot preparation and data collection | Stable pilot with anonymous, usable response data. |
| 13-16 | Analysis, report, and final demo | Results, documentation, polished deployment, and presentation. |

# Month 1: Foundation and core game

## Week 1: Scope and data setup

Person A - Frontend: Map one complete round: food card -> answer -> reveal -> score. Agree on the minimum screens.

Person B - Backend / Database: Choose the stack, create the project repository, and define the foods, sessions, and responses data fields.

Person C - Data / Research: Confirm the NOVA terminology, inspect the source dataset, and document the card-approval rules.

Definition of done: The team agrees on the game flow, data fields, and minimum feature list.

## Week 2: Prepare approved game cards and a static prototype

Person A - Frontend: Build one static 10-question page with four answer buttons and a score counter using temporary cards.

Person B - Backend / Database: Create the database schema and a repeatable import path for approved food cards.

Person C - Data / Research: Lead review of the 200 candidate cards. Split the work across the team and approve or reject cards with notes.

Definition of done: At least 100 approved cards exist, with at least 25 per NOVA level, and the static prototype can be clicked through.

## Week 3: Connect real data to the game

Person A - Frontend: Replace temporary cards with real data and show one random card at a time.

Person B - Backend / Database: Seed the approved foods table and build the endpoint that returns a question without exposing the answer first.

Person C - Data / Research: Check card balance, ingredient text, names, duplicates, and unclear examples. Finalize the initial data dictionary.

Definition of done: A player can complete a local round of 10 real food questions.

## Week 4: Finish the first complete game loop

Person A - Frontend: Add answer feedback, reveal content, a score summary, and restart behaviour.

Person B - Backend / Database: Save guessed level, actual level, response time, and anonymous session ID for every answer.

Person C - Data / Research: Write short and factual explanation text; do a full content check of every card currently seeded.

Definition of done: The team can demonstrate an end-to-end 10-question game and confirm that response records are saved correctly.

# Month 2: MVP completion and internal testing

## Week 5: Make the MVP reliable on mobile

Person A - Frontend: Improve responsive layout, loading states, and clear instructions for first-time players.

Person B - Backend / Database: Prevent repeated food cards within a round and validate all answer logging rules.

Person C - Data / Research: Replace weak or unfamiliar cards and maintain a balanced approved pool of at least 100 cards.

Definition of done: The game works cleanly on a phone and desktop browser with real cards.

## Week 6: Add minimal data collection and results support

Person A - Frontend: Improve the start, results, and replay screens. Keep the design simple and readable.

Person B - Backend / Database: Add anonymous sessions and a basic response export for later analysis. Do not build login unless required.

Person C - Data / Research: Define the metrics to report: accuracy by level, common wrong guesses, score, and response time.

Definition of done: A test round creates an exportable record with all research-relevant fields.

## Week 7: Deploy a staging version and test usability

Person A - Frontend: Polish accessibility, button labels, and mobile spacing. Fix only issues found in testing.

Person B - Backend / Database: Deploy a staging link and confirm the data path works outside the local computer.

Person C - Data / Research: Run a 5-10 person usability test and collect specific feedback on unclear cards or instructions.

Definition of done: A shareable staging link works and has a short prioritized feedback list.

## Week 8: MVP checkpoint

Person A - Frontend: Fix important usability issues; avoid adding new game modes or visual features.

Person B - Backend / Database: Fix data, deployment, and logging bugs discovered during usability testing.

Person C - Data / Research: Update the card list and wording based on feedback. Prepare a brief checkpoint summary for the professor.

Definition of done: The MVP is stable enough for a professor demo and pilot preparation.

# Month 3: Pilot preparation and data collection

## Week 9: Prepare the pilot without expanding scope

Person A - Frontend: Make only small clarity improvements and create a short in-game instruction screen.

Person B - Backend / Database: Add a simple safe import or update workflow only if changing approved cards is otherwise difficult.

Person C - Data / Research: Prepare participant instructions, a recruitment message, and consent text if required by the professor.

Definition of done: The team has a stable pilot build and a clear participant workflow.

## Week 10: Launch the pilot

Person A - Frontend: Support participants and fix only game-breaking problems.

Person B - Backend / Database: Monitor errors and validate that new response records are being stored and exported correctly.

Person C - Data / Research: Begin recruitment and track participation. Record any card complaints or obvious classification issues.

Definition of done: The first real participant responses are recorded successfully.

## Week 11: Continue data collection

Person A - Frontend: Keep the user experience stable; do not change game logic mid-pilot unless it is broken.

Person B - Backend / Database: Check for duplicate, incomplete, or corrupted response records and keep a clean export.

Person C - Data / Research: Continue recruitment and monitor response count against the target agreed with the professor.

Definition of done: The pilot has sufficient clean, usable responses or a clear plan to reach the target.

## Week 12: Close and prepare the data

Person A - Frontend: Freeze feature work and only correct critical bugs.

Person B - Backend / Database: Export the final response dataset and lock the code/data version used for the pilot.

Person C - Data / Research: Remove test records, document exclusions, and prepare the analysis-ready dataset.

Definition of done: The team has a clean, frozen dataset and knows exactly what will be analysed.

# Month 4: Analysis, report, and final demo

## Week 13: Analyze the game results

Person A - Frontend: Capture polished screenshots and help convert key findings into clear visuals.

Person B - Backend / Database: Generate tables for accuracy, guesses, response time, and most-misclassified foods.

Person C - Data / Research: Lead analysis by NOVA level and identify the foods players most often misunderstand.

Definition of done: A results draft exists with accurate tables and a small set of meaningful findings.

## Week 14: Write the report and presentation

Person A - Frontend: Prepare demo flow, screenshots, and visual consistency for the presentation.

Person B - Backend / Database: Document the database structure, deployment steps, and reproducible data workflow.

Person C - Data / Research: Write methods, results, limitations, data attribution, and conclusion for the report.

Definition of done: A complete first draft of the report and presentation exists.

## Week 15: Final quality review

Person A - Frontend: Perform a full gameplay test on mobile and desktop and rehearse the demo.

Person B - Backend / Database: Check deployment, data export, and recovery of the final version.

Person C - Data / Research: Check the report for terminology, source attribution, and consistency with the actual data.

Definition of done: The app, report, and slides are internally approved by all three members.

## Week 16: Submission buffer and presentation

Person A - Frontend: Handle final visual fixes and present the live game confidently.

Person B - Backend / Database: Be available for database and deployment questions during the demo.

Person C - Data / Research: Be available for methodology, data, and analysis questions during the demo.

Definition of done: The final deliverables are submitted, deployed, and ready to demonstrate.

# This week's checklist: Week 2

Keep this week focused. The goal is not a finished product. The goal is an approved initial card pool, a clickable static game screen, and a database structure ready to receive real cards.

Person A: build a static 10-question screen with four answer buttons and a score counter.

Person B: create the foods, sessions, and responses tables plus a simple food-card import path.

Person C: lead review of the 200 candidate cards. Each team member reviews roughly 65-70 cards and records approve/reject notes.

All three: meet at the end of the week, combine approved cards, and test one 10-question round together.